## Sprints
Sprint 1 9/17-9/30 | Tasks | Completeness | Information | Assign
| Flesh out Use Cases | Complete | Go over Use cases and eliminate ones that are not needed. | Everyone
| Work on UML | Complete | Design, create and work on UML | Everyone
| Get Familiar with qt | Complete | Look over QT framework, set it up on your machince. | Everyone
| Review SQL Database | Complete | Took the class last semester, have everyone review the material again and get a quick refresher. | Everyone
| Set up Github and a Repo | Complete | Set up the Repo and have everyone set up their git accounts. | Everyone
Sprint 2 10/1-10/14 | System Requirements | Complete | Going over use cases and talk/explain about system requirements for each. | Everyone
| Base of a Calendar UI | Complete | Get a working prototype of the application | Everyone
| ERD for Database | Complete | Create and Look over the ERD for our Database | Everyone
| Go over Signals and Slots* | Carry over to Sprint 3 | Review and look over Signals and Slots | Everyone
Sprint 3 10/15-10/28 | Insert tables into the Database | Complete | Adding Tables into the Database. Make sure the apporiate information is getting into the correct user, etc. | Chris Banci, Greg Seda
| Make sure button functions work | Complete | Make sure the Add Event, Delete Event, Edit Event buttons work. | Esmond Liang, Chris Morikawa
| Show events in the Tableview of a specific day | Complete | Make sure the event can be seen on the Calendar of the correct Day of the Month. Just show the Event Name. | Andrew Zhang, Malialosa Taupule
| Highlight event block | Complete | Have a date highlighted telling the user there is an event on that day | Katherine Mayo, Zena Nuhaily
| Go over Signals and Slots* | Complete |  | Everyone
Sprint 4 10/29-11/11 | Group List and Group Calendar | Complete | Creating a Group list, Group Calendar, and merge the events of members | Andrew Zhang, Malialosa Taupule, Katherine Mayo
| Creating Groups, Update Database for Group Members. | Almost Done push to next sprint. | Work on the database to work with groups, Make a discussion board, and creating reminders | Esmond Liang, Greg Seda, Chris Banci
| Work on the UI, showing the difference between group/personal Calendar, Home button functionality | Complete. | Just working on the Design and Layout of the Application, differentiate the calendar between the group and personal, and have home button functionality. | Chris Morikawa, Zena Nuhaily
Sprint 5 11/12 - 11/25 | Powerpoint Preparation |  | Organize and prepare for the ppt. | Everyone.
| Refactoring | Complete | Change of code, and/or clean up. | Everyone.
| Discussion board And Reminders | Complete | Continuing to work on Discussion Board. Continuing to work on Reminders. | Esmond Liang, Greg Seda, Chris Banci

## Backlog
Bug Title | Description of Bug | Reporter | Assign | Priority | Comments/Notes | Resolved? | Fix
Dulpicate Buttons | Multpie of the same button shows up on the dashboard(i.e. Two Edit Event buttons) | Greg Seda, Katherine Mayo, Esmond Lliang | Chris Morikawa |  | Greg -Some people were having issues seeing two buttons overlaping each other. | Yes | The fix was to go into the UI file and delete multiple buttons, I believe it happen during the merge of the two branches, when fixing the merge conflicts.
Highlight not Gone | When deleting an event from Calendar it still shows highlighted even with no events | Malia and Andrew | Malia and Andrew |  |  | Yes | Paint the cell white if no events are in the cell/date.
No Double Click for Event | When selecting the event from the table view, just single click not double click | Malia and Andrew | Chris Morikawa |  | Andrew- Just an annoying little workaround but would be nice for just single click | Yes | Switched to a single click
Not showing Login Screen | When starting up the application, it starts on Create user and not Login Screen. | Everyone | Chris Morikawa |  | Everyone- Why does it show only create first. | Yes | Just went to the UI in QT and just click on the tab of Login. After saving it, the login screen just shows and not the Create screen.
User is shown to be logged in, but really isn't | A user who is not currently logged in can still be shown as "Online" on other users list | Greg Seda | ? |  | Greg - a small bug, don't think it is a high priority based on the current timeline
Application crashed | The app crashed as I was testing each function in the app | Greg Seda | ? | ? | Greg - Not sure how important this is because it could just be my laptop. I'm the only one that has had this issue.
Press the X button, the color still paints the cell. | When adding an event on the calendar, when clicking on the X button it still shows the cell as an event was added. When clicking cancel it is fine. | Chris Morikawa |  |  |  | Yes | Dialog.cpp: override closeEvent() to set accept = false and close dialog
Multiple group events error | Group calendar displays group events as multiple events rather than one single group event. | Malia Taupule | Malia Taupule, Kathy Mayo, Andrew Zhang |  |  |  |  | Legend of Priority
Clicking group name doesn't displays group events | User must click on Group ID to display group events in events view | Chris Banci |  |  |  | Yes | Select whole row instead of cell, use selectedChanged signal | Low | Minor/Annoying (i.e minor text fix)
Application cannot minimize | minimize button missing from title bar | Chris Banci |  |  |  | Yes | Set window flags for min/max buttons | Medium | Workaround
[8 empty] | High | Not Working!

## Accomplished
Name | Tasks
Christopher Banci | Created and worked on Database, Login/Create screen, Dashboard/Calendar, worked on SRS, Requirments, helped implement threads, created weekly bulletin/reminders
Chris Morikawa | Created Wiki, Git Repository and managing Version Control, Backlog creation. Project Lead, Creating functionally of Edit and Delete button, worked on UI
Katherine Mayo | Helped created the UML, worked on SRS, Test Cases, group & personal calendar merge
Gregory Seda | Work on Database, worked on SRS, Test Cases, Requirements, weekly bulletin/reminders
Zena Nuhaily | Helped updated the Wiki, worked on the SRS, Test cases, Requirements, Worked on the UI
Esmond Liang | Helepd with SRS, Test Cases, Requirements, worked on Delete and Edit functions of buttons,
Andrew Zhang | Helped with SRS, Test Cases, Requirements, Worked on Selecting a day show up in the tableview, and highlighting feature on calendar cell, group & personal calendar merge
Malialosa Taupule | Helped with SRS, Test Cases, Requirements, Made the ERD for database, Worked on Selecting a day show up in the tableview, and highlighting feature on calendar cell, group & personal calendar merge